SUBCONTRACT

| SUBCONTRACT # | 1. HOST COUNTRY: Benin |  |  |  | 2. EFFECTIVE DATE: |  |
| --- | --- | --- | --- | --- | --- | --- |
| 3. PERIOD OF PERFORMANCE: 10/07/2011 THROUGH 30/11/2011 |  |  |  |  |  |  |
| SUBCONTRACTOR NAME & ADDRESS: Pr. Achille MASSOUGBODJI Laboratoire de Parasitologie du CNHU Faculté des Sciences de la Santé (FSS-UAC) Cotonou, BENIN Tel : Fax : E-mail: |  |  | PURPOSE OF SUBCONTRACT: Training for parasitemia testing, and microscopic examination of thick blood smears as part of the 2011 Benin DHS-EMICoV Survey (EDSIV-EMICoV 2011) TYPE OF SUBCONTRACT: Firm Fixed Price |  |  |  |
| 4. MACRO CHARGE CODE: 5. MACRO PRIME CONTRACT: 6. MACRO CLIENT AGENCY: USAID |  |  | 7.TOTAL SUBCONTRACT COST: US $34,000 8. AMOUNT FUNDED BY MACRO: N/A |  |  |  |
| CERTIFICATION OF CURRENT COST & PRICING DATA THE SUBCONTRACTOR CERTIFIES, BY SIGNING THIS SUBCONTRACT, THAT TO THE BEST OF THEIR KNOWLEDGE AND BELIEF, ALL OF THE COST & PRICING DATA USED IN THE NEGOTIATION OF THIS SUBCONTRACT ARE CURRENT, ACCURATE AND COMPLETE AS OF THE DATE OF SIGNATURE. |  |  |  |  |  |  |
| PART I - THE SCHEDULE TABLE OF CONTENTS: The following marked sections are contained in this Subcontract: |  |  |  |  |  |  |
| PART/SECTION TITLE |  | Page |  | PART/SECTION TITLE |  | Page |
| PART I - THE SCHEDULE [x] A SUBCONTRACT COVER [x] B SUPPLIES/SERVICES & COST/PRICES [x] C WORK DESCRIPTION/SPECIFICATIONS [ ] D PACKAGING & MARKING [x] E INSPECTION & ACCEPTANCE [x] F DELIVERIES & PERFORMANCE [x] G CONTRACT ADMINISTRATION [x] H SPECIAL PROVISIONS |  | 01 02 02 03 04 04 06 |  | PART II [x] I GENERAL PROVISIONS PART III [x] A – Budget [x] B – Timetable [x] C - Clauses Incorporated by Reference |  | 12 16 18 19 |
| IMPORTANT NOTICE PARTIES TO THIS SUBCONTRACT SHOULD EACH RETAIN A COPY OF THIS AWARD SHEET CONTAINING THEIR ORIGINAL SIGNATURES. THE TERMS OF THIS SUBCONTRACT WILL NOT BECOME BINDING UNTIL BOTH PARTIES HAVE AFFIXED THEIR RESPECTIVE SIGNATURES. ALL INVOICING AND CORRESPONDENCE MUST REFERENCE THE SUBCONTRACT NUMBER, AND THE CHARGE CODE. |  |  |  |  |  |  |
| SUBCONTRACT OF THE PARTIES Subcontractor agrees to furnish and deliver all items and to perform all of the services specified herein for the monetary consideration set forth above. The rights and obligations of the parties to this Subcontract shall be subject to and be governed by the following documents in the order listed: (a) This Subcontract Award Sheet, (b) The Subcontract Schedule, (c) The General Provisions. (d) The Solicitation, if any (e) The Macro Prime Contract and (f) Such other provisions, representations, exhibits, certifications, and attachments as may be incorporated in full referenced herein. In the event of a conflict between the terms and conditions of this document and any agreement of Subcontractor, whether incorporated or not into this Subcontract, then the provisions of the Subcontract shall govern. |  |  |  |  |  |  |
| Signature and Date Pr. Achille MASSOUGBODJI, Chef de Service Laboratoire de Parasitologie, Faculté des Sciences de la Santé Université d’Abomey-Calavi |  |  |  | Signature and Date |  |  |

Statement of Work

The 2011 Benin DHS - EMICoV Survey (EDS IV – EMICoV 2011) is being undertaken to obtain current estimates of key indicators needed to measure progress toward the achievement of the Government of Senegal’s goals in population, health and nutrition.

The 2011 DHS-EMICoV will cover a sample of 750 clusters (approximately 18,000 households and 10,000 women age 15-49 years old).  In addition, a sub-sample of one-third of the total of households in the sample will be selected in which all men age 15-59 years will be eligible.  All women and all men eligible for the survey in this sub-sample of households will also be eligible for the HIV test.  Moreover, in this sub-sample of households, all women and all men eligible for the survey as well as all children under 5 years of age will be eligible for the anemia test.  Finally, in this household sub-sample, all children under age 5 will be eligible for parasitemia testing, and all women eligible for the survey as well as all children under age 5 will be eligible to be measured and weighed in order to determine their nutritional status.

The Institut National de la Statistique et de l’Analyse Economique (INSAE) will be responsible for implementing the  2011 DHS-EMICoV Survey (EDS IV – EMICoV 2011). ICF Macro and its technical partners :  The Programme National de Lutte contre le Sida (PNLS), le Programme National de Lutte contre le Paludisme, le laboratoire de Parasitologie, de la Faculté des Sciences de la Santé (FSS) de l’Université d’Abomey-Calavi (Parasitology laboratory) will provide technical assistance through its contract with the United States Agency for International Development (USAID). This assistance concerns all aspects of the survey: preparation of questionnaires and manuals, training of field personnel data processing programs and tabulation, data analysis, laboratory testing and analysis (HIV and parasitemia) and data dissemination

Under le laboratoire de Parasitologie, de la Faculté des Sciences de la Santé (FSS) de l’Université d’Abomey-Calavi (Parasitology laboratory) was selected to:

1) Train field staff of the 2011 DHS-EMICoV Survey (EDS IV – EMICoV 2011) on how to collect blood from children under 5 years old, and how to use the Rapid Diagnostic Test devise for the detection of all malarial parasites;

2) Train field staff of the 2011 DHS-EMICoV Survey (EDS IV – EMICoV 2011) on how to collect thick blood smear on a microscopic slide from children under 5 years old;

3) Supervise field activities;

5) Undertake microscopic examination of approximately 6,000 samples of thick blood smears from children under 5 years old as well as data entry and analysis.

6) 300 samples (5% of all the samples) will be sent to a referency parasitology for quality assurance.

Timetable

July 19, 2011 – May 15, 2012

| Activities | Dates |
| --- | --- |
| Signing subcontract | July 19, 2011 |
| Training of field staff on how to collect blood for pretest | August 9-11, 2011 |
| Training of field staff on how to collect blood for pretest | September 13-15, 2011 |
| Supervision of field activities | October 5, 2011 – January 31, 2012 |
| Microscopic examination of thick blood smears | October 20, 2011 – February 25, 2012 |
| Entry of the microscopic examination results | October 20, 2011 – February 25, 2012 |
| Data analysis | November 11-May 15, 2012 |

PAYMENT SCHEDULE

| Task No. | Task Description | Acceptance Criteria |  | Payment |
| --- | --- | --- | --- | --- |
| 1 | To have 6 trainers (4 lab technicians and 2 senior professionals) from the Lab de Parasitologie participate in the training of field staff on how to collect blood for and parasitemia testing. | Training of field personnel and monitoring field activities during the main survey | August 15, 2011 | $15,000 |
| 2 | Completion of microscopic examination of approximately 4,500 samples of thick blood smears from children under 5 years old and data entry of the test results | Receipt by INSAE & Macro of the data files with the microscopic examination results | October 15, 2011 | $16,000 |
| 3 | Completion of data analysis of the parasitemia testing | Receipt by INSAE& Macro of the chapter on the parasitemia testing using the thick and thin blood smears | May 10,2011 | $4,860 |

Benin DHS - EMICoV Survey

(EDS IV – EMICoV 2011)

Activities of the Laboratoire de Parasitologie

| Description | Nber | Quantity | Unit Cost | Total | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | x 1000 CFA | x 1000 CFA | US $ |  |
| TRAINING OF FIELD STAFF |  |  |  |  |  |  |  |
| Trainers |  |  |  |  |  |  |  |
| Lab. technicians | 4 | 8 | days | 15 | 480 | 960 |  |
| Senior lab professionals | 2 | 8 | days | 30 | 480 | 960 |  |
| S/Total |  |  |  |  | 960 | 1 920 |  |
| SUPERVISION OF FIELDWORK |  |  |  |  |  |  |  |
| Lab. technicians | 2 | 15 | days | 40 | 1 200 | 2 400 |  |
| Senior lab professionals | 2 | 15 | days | 65 | 1 950 | 3 900 |  |
| S/Total |  |  |  |  | 3 150 | 6 300 |  |
| MICROSCOPIC EXAMINATION OF 6000 BLOOD SMEARS |  |  |  |  |  |  |  |
| Lab. technicians | 4 | 3,5 | months | 340 | 4 760 | 9 520 |  |
| Senior lab professionals | 2 | 3,5 | months | 1000 | 7 000 | 14 000 |  |
| Furniture/Materials (water, etc.) | 1 | 1 | months | 80 | 80 | 160 |  |
| S/Total |  |  |  |  | 11 840 | 14 160 |  |
| DATA ENTRY AND ANALYSIS |  |  |  |  |  |  |  |
| Data entry clerk | 1 | 20 | days | 10 | 200 | 400 |  |
| Data entry supervisor | 1 | 10 | days | 15 | 150 | 300 |  |
| Data analysts | 2 | 10 | days | 35 | 700 | 1 400 |  |
| S/Total |  |  |  |  | 1 050 | 1 700 |  |
| GRAND TOTAL |  |  |  |  | 17 000 | 35 860 |  |